## Bar coad Shedule
WORK | MARCH |  |  | APR |  |  | MAY |  |  | JUN | JULY | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | Date Of Period (Completion)
4th floor roof | 1st | [17 empty] | Dt;19/03/20
5th floor columns |  | 2nd | [16 empty] | Dt;25/03/20-26/03/20
5th floor roof |  |  | 3rd | 1st | [14 empty] | Dt;28/03/20-Dt;08/04/20
1st floor
BW | [18 empty] | Dt;31/03/20
1st coat internal plas |  |  |  |  | 2nd | 3rd | 1st | [11 empty] | Dt;09/04/20-30/04/20
2nd coat internal plas | [18 empty] | Dt;22/06/20 -24/06/20
electrical chipping and boxing | [18 empty] | Dt;26/03/20-31/03/20
drainage/plumbing internal | [18 empty] | 27/06/20 & 18/06/20
false ceiling
wiring | [18 empty] | 22/06/20 & 10/08/20
internal putty | [18 empty] | 06/08/20 & 16/09/20
flooring tiles | [18 empty] | 4/01/21-31/01/21
wall tiles
painting
doors
window fixings
sanitary and CP fitings
door polish
door painting
MCB and switches
railings | [18 empty] | 4/01/21-31/01/21 &7/02/21
2nd floor
BW | [18 empty] | Dt:30/03/20
1st coat internal plas | [6 empty] | 1st | [11 empty] | Dt:30/04/20 & 8/04/20
2nd coat internal plas | [18 empty] | Dt:12/06/20
electrical chipping and boxing | [18 empty] | Dt:31/03/20
drainage/plumbing internal | [18 empty] | Dt:24/06/20 & 12/07/20
false ceiling
wiring | [18 empty] | Dt:22/06/20 & 10/07/20
internal putty | [18 empty] | Dt:26/07/20 & 12/08/20
flooring tiles | [18 empty] | Dt:31/01/21 & 06/01/21
wall tiles
painting
doors
window fixings
sanitary and CP fitings
door polish
door painting
MCB and switches
railings | [18 empty] | Dt:31/01/21 & 06/01/21
3rd floor
BW | [18 empty] | Dt;30/03/20 & 10/04/20
1st coat | [7 empty] | 2nd | 3rd | [9 empty] | Dt;18/05/20 & 07/06/20
2nd coat | [18 empty] | Dt:02/07/20
electrical chipping and boxing | [18 empty] | Dt:24/04/20
drainage/plumbing internal | [18 empty] | Dt:19/07/20 & 14/08/20
false ceiling
wiring | [18 empty] | Dt:19/07/20 & 14/08/20
putty | [18 empty] | Dt:26/08/20 & 14/09/20
flooring tiles | [18 empty] | Dt:09/01/21-31/01/21 & 07/02/21
wall tiles
painting
doors
window fixings
sanitary and CP fitings
door polish
door painting
MCB and switches
railings | [18 empty] | Dt:09/01/21-31/01/21 & 07/02/21
4th floor
BW | [18 empty] | Dt31 /03/20 &14/04/20
1st coat | [7 empty] | 2nd | 3rd | [9 empty] | Dt:16/05/20 &14/06/20
2nd coat | [18 empty] | Dt:11/07/20
electrical chipping and boxing | [18 empty] | Dt;24/04/20
drainage/plumbing internal | [18 empty] | Dt:23/07/20 &14/08/20
false ceiling
wiring | [18 empty] | Dt:1/10/20-30/10/20
putty | [18 empty] | Dt:27/08/20-18/09/20
flooring tiles | [18 empty] | Dt:11/01/21-31/01/21 & 07/02/21
wall tiles
painting
doors
window fixings
sanitary and CP fitings
door polish
door painting
MCB and switches
railings | [18 empty] | Dt:13/01/21-31/01/21 & 07/02/21
5th floor
BW | [6 empty] | 1st | 2nd | [10 empty] | Dt:24/04/20 & 14/05/20
1st coat plas | [18 empty] | Dt:24/06/20 & 09/07/20
2nd coat plas | [18 empty] | Dt:11/08/20
electrical chipping and boxing | [8 empty] | 3rd | [9 empty] | Dt:21/05/20
drainage/plumbing internal | [18 empty] | Dt:22/07/20 &16/08/20
false ceiling
wiring | [18 empty] | Dt:01/10/20-30/10/20
putty | [18 empty] | Dt:06/09/20-18/10/20
flooring tiles | [18 empty] | Dt:15/01/21-31/01/21 & 07/02/21
wall tiles
painting
doors
window fixings
sanitary and CP fitings
door polish
door painting
MCB and switches
railings | [18 empty] | Dt:18/01/21-31/01/21 & 07/02/21
EXTERNAL
elevation 1st coating plas | [18 empty] | Dt:01/06/20-30/06/20
remaning exterior 1st coating plas | [18 empty] | Dt:05/06/20-30/06/21
elevation 2nd coating plas | [18 empty] | Dt:27/07/20 &07/08/20
remaning exterior 2nd coating plas | [18 empty] | Dt:27/07/20 &07/08/20
drainage external | [18 empty] | Dt:30/07/20 &07/08/20
putty external | [18 empty] | Dt:24/10/20-30/11/20
painting external | [18 empty] | Dt:18/12/20 & 08/01/21
common amenities
1st floor
corridor flooring | [18 empty] | Dt:01/12/20-31/12/20 &08/01/21
stair case
lift works
electrical
false ceiling
painitng
2nd floor
corridor flooring | [18 empty] | Dt:01/12/20-31/12/20 &08/01/21
stair case
lift works
electrical
false ceiling
painitng
3rd floor
corridor flooring | [18 empty] | Dt:01/12/20-31/12/20 &08/01/21
stair case
lift works
electrical
false ceiling
painting
4th floor
corridor flooring | [18 empty] | Dt:01/12/20-31/12/20 &08/01/21
stair case
lift works
electrical
false ceiling
painting
5th floor
corridor flooring | [18 empty] | Dt:01/12/20-31/12/20 &08/01/21
stair case
lift works
painting
Cellar
RW 1st coat plastering
RW 2nd coat plastering
ceiling 1st coat
ceiling 2nd coat
electrical wiring
VDF flooring
waste water Collection pit
staircase
stilt
BW office & security room
pl 1st coat column & ceiling
pl 2nd coat column & ceiling
VDF flooring
compound wall basement
compound wall BW
compound wall plastering
compound wall putty
Main Gate
painting
stair case railing